223-16
October 6, 2016
R E S O L U T I O N

	WHEREAS, the Township Council by Resolution No. 215-15 dated August 11, 2015 awarded the contract Street Improvements, Phase II, 2015 Re-Bid in the amount of $3,086,160.43 to Reggio Construction, Inc., 1575 West Street, Fort Lee, N.J. 07024; and
	WHEREAS, this contract included improvements to 21 streets totaling about 3.25 miles in length; and
	WHEREAS, the Township Council by Resolution No. 274-15 dated November 24, 2015 authorized Change Order No. 1 to this contract in the amount of $15,000.00; and
	WHEREAS, the Township Council by Resolution No. 195-16 dated August 9, 2016 authorized Change Order No. 2 to this contract in the amount of $293,400.00; and
	WHEREAS, one of the 21 streets included Overlook Avenue from Lawrence Avenue to Luddington Road; and
	WHEREAS, the Municipal Engineer advised the Township Council of the desire by residents of Overlook Avenue to remove nine large and mature shade trees and then improve the block of Overlook Avenue between Ridgeview Avenue and Luddington Road with granite block curb and concrete driveway aprons which were not part of the original contract; and
	WHEREAS, the Municipal Engineer recommends Change Order No. 3 be approved with Reggio Construction Inc. to improve Overlook Avenue between Ridgeview Avenue and Luddington Road with new granite block curb and concrete driveway aprons under the 2015 contract prices; and
	WHEREAS, the estimated cost for these additional improvements under Change No. 3 to the contract Street Improvements Phase II, 2015, Re-Bid is $76,500.00; and
	WHEREAS, Change Order No. 3 in conjunction with Change Orders No. 1 and No. 2 amount to a 12.47 percent in the original contract amount; and
	WHEREAS, sufficient funds exist for the additional work under Change Order No. 3; and
	WHEREAS, the Township Council concurs in the foregoing.
[bookmark: _GoBack]	NOW THEREFORE BE IT RESOLVED by the Township Council of the Township of West Orange that Change Order No. 3 for the contract Street Improvements, Phase II, 2015, Re-Bid with Reggio Construction, Inc., 1575 West Street, Fort Lee, New Jersey 07024 in the amount of $76,500.00 representing in conjunction with Change Order No. 1 and No. 2 a 12.47 percent increase in the original contract amount to improve portions of Overlook Avenue between Ridgeview  Avenue and Luddington Road with granite block curb and concrete driveway aprons is hereby approved.


													
KAREN J. CARNEVALE, MUNICIPAL CLERK		VICTOR CIRILO, COUNCIL PRESIDENT

Adopted:  September 20, 2016


I hereby certify funds are available from: 	ACCOUNT NO. 03-2475-16-0060-010
					 	2016 STREET RESURFACING



						
JOHN GROSS, CHIEF FINANCIAL OFFICER


