351-23

October 10, 2023

R E S O L U T I O N

WHEREAS, by Resolution No. 99-22 dated April 5, 2022, the Township Council awarded the Contract Rock Spring Golf Club Cart Path Improvements to Grabowski Construction, Inc., 770 Northfield Avenue, West Orange, NJ 07052 in the amount of $944,475.00; and 

WHEREAS, at the elevated green near the No. 15 hole of the Rock Spring Golf Club golf course, a wall collapsed causing damage to the cart path; and 

WHEREAS, it was necessary to reconstruct the wall and the cart path; and  

WHEREAS, the wall was reconstructed in a manner in which it will not occur again; and
WHEREAS, the Assistant Municipal Engineer by letter dated August 30, 2023 recommends additional funding in the amount of $15,035.02 for the reconstruction of the wall and cart path at the Rock Spring Golf Club; and 

WHEREAS, sufficient funds exist for this additional work; and 
WHEREAS, the Township Council concurs in the foregoing.

NOW THEREFORE BE IT RESOLVED by the Township Council of the Township of West Orange that Change Order No. 1 and Final for the Rock Spring Golf Club Cart Path Improvements with Grabowski Construction, Inc., 770 Northfield Avenue, West Orange, NJ in the amount of $15,035.02 or 1.59 percent increase in the original contract amount is hereby approved bringing the adjusted contract amount to $959,510.02.

BE IT FURTHER RESOLVED that the Municipal Engineer is authorized to execute the Change 

Order on behalf of the Township of West Orange.

Karen J. Carnevale, RMC, Municipal Clerk

Tammy Williams, Council President
Adopted: October 10, 2023
I hereby certify funds are available
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2021 Capital Budget 

Rock Spring golf Club 
$14,995.02

John Gross, Chief Financial Officer
